## Activity List
MS | STD | OBJ | ABBR | ASSIGNED TEAM / SPRINTS & SUB-ACTIVITIES | START | END | DAYS | RESOURCES | PREDECESSOR
CISCO STANDARDS INTEGRATION TEAM
|  |  | K1 | Develop contracts between Cisco and manufacturer to confirm scope of compliance and responsibilities | 2023-01-01 | 2023-01-07 | 7 | Legal, IT leaders | None
| S |  |  | Contract between Cisco and manufacturer determines scope and standards for reporting, auditing, patching, and incident response
|  | 2.3 | K2 | Develop contracts and standards for implementation of HBOM/SBOM with suppliers. | 2023-01-01 | 2023-01-07 | 7 | Legal, IT leaders | S1
| S | 2.1 |  | SBOM/HBOM meets all minimums listed by Dept. of Commerce publication "The Minimum Elements for a Software Bill of Materials" 12 JUL 2021.
M |  |  |  | All contracts are signed by Cisco and Manufacturer.
M |  |  |  | All relevant procedures, guidance, and Cisco standards are published
TRAINING TEAM
|  |  | T1.00 | Develop training curriculum and schedule for manufacturer's IT staff focusing on modifications to their infrastructure, software, and procedures. | 2023-01-22 | 2023-02-11 | 14 |  | K1, N2, D1, P5
|  |  | T2.00 | Prepare instructors, training aids and familiarize with systems. | 2023-02-12 | 2023-03-04 | 14 |  | T1, K2
|  |  | T3.00 | Execute training classes and complete practical tests on procedures. | 2023-03-12 | 2023-03-18 | 7 |  | T2
M |  |  |  | Manufacturer completes IT staff employee training, including a satisfactory incident response exercise / patching test.
M |  |  |  | Handoff systems operations/maintenance to manufacturer's IT team
| S |  |  | Training scope for IT: new hardware devices, monitoring and patching software, procedures auditing/reporting/patching/incident response
| S |  |  | Training scope for users/IT: requirements for system access, AUP
NETWORK MONITORING TEAM
|  | 1.3 | N1.00 | Identify and account the current manufacturer network systems/topology. | 2023-01-08 | 2023-01-21 | 14 |  | K1
|  | 1.6 | N1.01 | Develop a heat map of wireless access points. | 2023-01-08 | 2023-01-08 | 1
M |  | 1.3 |  | The manufacturer's on premises IT infrastructure is inventoried and accounted.
|  |  | N2.00 | Assess the manufacturer's needs and develop a plan for necessary modifications to the network systems/topology to support network monitoring. | 2023-01-22 | 2023-01-28 | 7 |  | N1
M |  |  |  | Manufacturer and Cisco approve updated network topology plan
|  |  | N3.00 | Procure new network monitoring hardware/software systems to be integrated into manufacturer network. | 2023-01-29 | 2023-02-04 | 7 | Procurement, activity by outside party | N2
|  |  | N4.00 | Install and test new network monitoring hardware/software. | 2023-02-05 | 2023-02-11 | 7 |  | N3
M |  |  |  | All new network hardware devices and supporting software are installed and tested.
| S | 1.6 |  | Ensure that all wireless access points to prevent off-premises connections, create heat map
| S | 1.7 |  | Ensure network connections (ethernet, VPN, wireless) use secure protocols
| S | 1.4 |  | Segregate production, development, and public-facing environments/networks.
DEVICE ONBOARDING & INVENTORY MANAGEMENT TEAM
|  |  | D1.00 | Identify automation solution for device onboarding and inventory management that supports manufacturer use case. | 2023-01-22 | 2023-01-28 | 7 |  | N1
|  | 1.1 | D2.00 | Establish on/off-boarding procedures for company, contractor and employee devices. | 2023-01-29 | 2023-02-04 | 7 |  | D1
|  |  | D3.00 | Procure, install, and test software systems for device onboarding and inventory management. | 2023-02-05 | 2023-02-11 | 7 |  | D2, N4
M |  |  |  | Manufacturuer has on-demand tracking of IT infrastructure.
| S | 1.2 |  | Onboarded host devices will have an installed agent to report security posture/compliance to a centralized system.
| S |  |  | Devices are recorded in inventory by assigned department / custodian.
| S |  |  | User devices report GPS location and are geofenced.
| S | 2.2 |  | Test new devices and software before integration into the network or manufacturing
PATCHING COMPLIANCE TEAM
|  | 4.2 | P1.00 | Identify automation solution for a patch pipeline to push to manufacturer devices. | 2023-01-22 | 2023-01-28 | 7 |  | N1
|  |  | P2.00 | Procure and install software systems for device patching. | 2023-01-29 | 2023-02-04 | 7 |  | P1
|  | 4.5 | P3.00 | Configure a quarantine network to redirect non-compliant systems for patch remediation. | 2023-02-05 | 2023-02-18 | 14 |  | N1
|  |  | P4.00 | Develop modifications as necessary to customize the patching solution for the manufacturer. | 2023-02-19 | 2023-02-25 | 14
|  |  | P5.00 | Publish patch management procedures. | 2023-02-26 | 2023-03-04 | 7 |  | P1, P4
M |  |  |  | Manufacturer tests onboarding / quarantine of new devices
| S | 4.4 |  | Automate security posture/patch compliance check upon login to internal network.
| S | 4.6 |  | Automate patch notification to all customers.
| S |  |  | 100% of on-premises equipment are patched within 24 hours of approval of patch.
| S | 1.5 |  | All environments have systems to reject access to devices not onboarded.
| S | 4.1 | A | Develop procedures to test patches in the development environment.
SUPPLIER ENGAGEMENT TEAM
|  |  | S1.00 | Develop and test Cisco HBOM/SBOM reporting standards, reporting templates, and tracking systems. Develop screening criteria for new suppliers. | 2023-01-01 | 2023-01-07 | 7
|  |  | S2.00 | Identify the primary suppliers (for critical components/software) to the manufacturer and perform a prelimiary assessment of supply chain risk. | 2023-01-08 | 2023-01-21 | 14 |  | N1
|  |  | S3.00 | Contact primary suppliers and negotiate to acquire their HBOM/SBOM. Provide technical assistance and deep research as needed. | 2023-01-22 | 2023-02-04 | 14 |  | S2
|  |  | S4.00 | Develop recommendations for alternative suppliers and investigate against screening criteria. | 2023-02-05 | 2023-02-18 | 14 |  | S1, S2
|  |  | S5.00 | Develop contingencies/controls to quality check suppliers that do not meet Cisco standards. | 2023-01-22 | 2023-02-04 | 14 |  | S1, S2
|  |  | S6.00 | Deveop finalized list of authorized suppliers and procure senior management sign-off. | 2023-02-05 | 2023-02-11 | 7 |  | S2, S3, S4
|  |  | S6.01 | Test HBOM/SBOM reporting to integrate across the suppliers, manufacturer, and Cisco HBOM/SBOM. | 2023-02-10 | 2023-02-10 | 1 |  | S1, S2
M |  |  |  | Manufacturer publishes a preliminary HBOM/SBOM for router/switch.
| S | 2.1 |  | SBOM/HBOM meets all minimums listed by Dept. of Commerce publication "The Minimum Elements for a Software Bill of Materials" 12 JUL 2021.
RISK ASSESSMENT TEAM
|  | 3.2 | R1.00 | Establish and procedures to receive threat/vulnerability updates for its IT infrastructure | 2023-01-08 | 2023-01-21
|  | 3.1 | R2.00 | Develop a risk assessment / register for the top three vulnerabilities and threats associated with router manufacturing and its supply chain risks | 2023-01-22 | 2023-02-04 |  |  | N1, S2
|  | 3.3 | R3.00 | Conduct an exercise testing threat/vulnerability update and notifications. | 2023-03-05 | 2023-03-11 |  |  | R2, P5
M |  |  |  | The manufacturer successfully tested theat/vulnerability update and notifications.
| S | 3.3 |  | The manufacturer incident response procedures and reporting synchronize and feed into Cisco’s incident response infrastructure.